## Slide 1
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
COMMON
ALTITUDE
TEAM AND CO-PRODUCER DISCUSSION
Paid scopes, roles and delivery requirements.
ORIGINAL CONCEPT GRAPHIC
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
01 / 12
Notes: Executive producers, specialist leads and potential co-producers
COMMON ALTITUDE
TEAM AND CO-PRODUCER DISCUSSION
Paid scopes, roles and delivery requirements.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 2
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Proposed founding functions
Hours, fees, availability and authority still need agreement.
Artistic +
relationships
Curatorial thesis, artists,
galleries and market
credibility.
Product + program
Digital/service requirements,
evidence and cross-functional
coordination.
Brand + design
Positioning, identity and
coherent physical/digital
communication.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
02 / 12
Notes: Executive producers, specialist leads and potential co-producers
Proposed founding functions
Hours, fees, availability and authority still need agreement.
Artistic + relationships / Curatorial thesis, artists, galleries and market credibility.
Product + program / Digital/service requirements, evidence and cross-functional coordination.
Brand + design / Positioning, identity and coherent physical/digital communication.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 3
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
First specialist roles
The project needs experienced delivery, collector sales and finance leads.
Executive producer
Comparable complex-venue
delivery. Authority and stop
rights.
Collector lead
Qualified demand,
appointments, seller
conversion and service.
Finance/controller
Cash, restrictions, contracts,
reconciliation and
independent challenge.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
03 / 12
Notes: Executive producers, specialist leads and potential co-producers
First specialist roles
The project needs experienced delivery, collector sales and finance leads.
Executive producer / Comparable complex-venue delivery. Authority and stop rights.
Collector lead / Qualified demand, appointments, seller conversion and service.
Finance/controller / Cash, restrictions, contracts, reconciliation and independent challenge.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 4
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Fees, scope and additional bonuses
Agree funded work first. Define any performance or profit participation separately.
No indefinite unpaid-production expectation.
Classification, fees, rights, milestones and cancellation agreed.
Founder equity and an event bonus are different matters.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
04 / 12
Notes: Executive producers, specialist leads and potential co-producers
Fees, scope and additional bonuses
Agree funded work first. Define any performance or profit participation separately.
No indefinite unpaid-production expectation.
Classification, fees, rights, milestones and cancellation agreed.
Founder equity and an event bonus are different matters.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 5
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Paid discovery stage
Begin work only after agreeing the scope and securing usable funds.
$75,000
Discovery underwriting target
$70,000
Defined work envelope
6 weeks
Proposed evidence/decision
period
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
05 / 12
Notes: Executive producers, specialist leads and potential co-producers
Paid discovery stage
Begin work only after agreeing the scope and securing usable funds.
$75,000 / Discovery underwriting target
$70,000 / Defined work envelope
6 weeks / Proposed evidence/decision period
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 6
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Core delivery fee budgets
These proposed amounts need contracts, hours and worker-classification review.
$260,000
Core-team delivery fees
$200,000
Artist/program fees
$1,550,000
Total proposed core cost
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
06 / 12
Notes: Executive producers, specialist leads and potential co-producers
Core delivery fee budgets
These proposed amounts need contracts, hours and worker-classification review.
$260,000 / Core-team delivery fees
$200,000 / Artist/program fees
$1,550,000 / Total proposed core cost
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 7
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Proposed allocation of 60 spaces
Site evidence must support the footprint. Smaller and larger options need separate budgets.
24
Gallery rooms
12
Artist salons
6
Signature briefs
18
Learning, common and support
PROPOSED PROGRAM FUNCTIONS / SITE SURVEY PENDING
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
07 / 12
Notes: Executive producers, specialist leads and potential co-producers
Proposed allocation of 60 spaces
Site evidence must support the footprint. Smaller and larger options need separate budgets.
24 / Gallery rooms
12 / Artist salons
6 / Signature briefs
18 / Learning, common and support
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 8
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Professional candidates
The project has appointed none of these candidates.
Two Parts
Potential production
discovery.
Jensen Hughes
Potential local
code/accessibility/fire scope.
UOVO Denver
Potential art-handling/logistics
scope.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
08 / 12
Notes: Executive producers, specialist leads and potential co-producers
Professional candidates
The project has appointed none of these candidates.
Two Parts / Potential production discovery.
Jensen Hughes / Potential local code/accessibility/fire scope.
UOVO Denver / Potential art-handling/logistics scope.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 9
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Funding and approval sequence
Site evidence, usable cash and accepted responsibilities control the schedule.
G0–G1
Fund discovery.
Establish site
feasibility.
G2–G3
Accept delivery
roles. Prove launch
finance/site path.
G4–G5
Fund/clear program
and authorize build.
G6–G7
Rehearse, inspect
and open only ready
approved areas.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
09 / 12
Notes: Executive producers, specialist leads and potential co-producers
Funding and approval sequence
Site evidence, usable cash and accepted responsibilities control the schedule.
G0–G1 / Fund discovery. Establish site feasibility.
G2–G3 / Accept delivery roles. Prove launch finance/site path.
G4–G5 / Fund/clear program and authorize build.
G6–G7 / Rehearse, inspect and open only ready approved areas.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 10
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Preview, public days and close
The proposed week runs August 9–15, 2027. Budget preparation and restoration separately.
PREVIEW
Orientation and professional
attention.
PUBLIC
Five days of free core art and
optional deeper programs.
CLOSE
Art care, restoration,
settlement and learning.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
10 / 12
Notes: Executive producers, specialist leads and potential co-producers
Preview, public days and close
The proposed week runs August 9–15, 2027. Budget preparation and restoration separately.
PREVIEW / Orientation and professional attention.
PUBLIC / Five days of free core art and optional deeper programs.
CLOSE / Art care, restoration, settlement and learning.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 11
THE NEXT DECISION
Role and capacity discussion
A paid discovery scope would define competence, availability, cost,
authority and risk.
Bring comparable delivered-work evidence and references.
Identify the conditions you need to deliver well.
Agree funded scope before recruitment or public credit.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
11 / 12
Notes: Executive producers, specialist leads and potential co-producers
Role and capacity discussion
A paid discovery scope would define competence, availability, cost, authority and risk.
Bring comparable delivered-work evidence and references.
Identify the conditions you need to deliver well.
Agree funded scope before recruitment or public credit.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.

## Slide 12
EXECUTIVE PRODUCERS, SPECIALIST LEADS AND POTENTIAL CO-PRODUCERS
Planning records and role agreements
The package includes 365 daily actions, 53 weekly records and finance, program and operating documents.
Candidate biographies do not establish capacity or willingness.
This deck creates no staffing, fee, equity or profit-share agreement.
Actual accepted roles and private counterpart details belong in controlled operational records.
COMMON ALTITUDE / 2027
WORKING PROPOSAL / 24 OCT 2026
12 / 12
Notes: Executive producers, specialist leads and potential co-producers
Planning records and role agreements
The package includes 365 daily actions, 53 weekly records and finance, program and operating documents.
Candidate biographies do not establish capacity or willingness.
This deck creates no staffing, fee, equity or profit-share agreement.
Actual accepted roles and private counterpart details belong in controlled operational records.
Status: working proposal. Site, dates, partners, funding and capacity need confirmation. The deck grants no external-action authority.
Financial source: data/project.json and generated financial-results.json.
Primary venue reference: https://www.denverenergycenter.com/home
Program/market/rights sources and individual candidate evidence: RESEARCH.md in the accompanying package.